## Inputs
Parameter | Value | Unit | Source/Note
Food boundary | dry kibble + limited freeze-dried |  | Frozen from handoff
Particle size | 5-15 | mm | EVT must verify
Freeze-dried ratio | <=20 | % volume | Planning input only
Usable capacity target | 3.35 | L | Rechecked in V0.1C proxy
Hopper OD variants | 180 / 185 | mm | EVT comparison

## Clearance Matrix
See CSV | rotor_window_channel_clearance_matrix_v01c.csv

## EVT Matrix
Test ID | Purpose | Sample | Pass Gate
EVT-FLOW-01 | Dose repeatability by food type | A/B/C rotor x window x channel | CV and jam rate below agreed threshold
EVT-WASH-01 | Wash/rinse/dry cycle | washable hopper + rotor + liner | No retained odor, visible residue, or seal damage
EVT-LOCK-01 | Quick-release retention and misuse | dual-side + center-lever | No accidental release under defined load

## DFMEA
Item | Failure Mode | Effect | Cause | S | O | D | RPN | Action
Rotor | Jam with 15 mm irregular food | Missed feeding | passage too small / freeze-dried shape | 9 | 5 | 4 |  | Run clearance + EVT flow matrix
Chute liner | Residue trapped near latch | Hygiene risk | dead corner / insufficient radius | 8 | 4 | 5 |  | OEM DFM + wash residue test
Quick release | Accidental release | spill / pet access | magnet-only retention or weak latch | 8 | 3 | 4 |  | Mechanical lock retention test
Load cell | Overload drift | wrong dose feedback | no hard stop | 7 | 4 | 5 |  | Add overload stop and bench test

## OEM RFQ Checklist
Attachment | Purpose | Status
V0.1C geometry STL/SVG | Discuss DFM, tool split, latch geometry | Ready for discussion, not production data
Risk register | Align engineering unknowns | Ready
EVT matrix | Quote prototype and test support | Ready
Material candidates | Confirm food-contact compliance | OEM/lab required

## Gate Review
Gate | Requirement | V0.1C Status
Digital geometry generated | All V0.1C STL/SVG files present | Pass
Clearance proxy | All combinations checked for 15 mm proxy | Pass with caveat
Physical validation | Real food / wash / torque / noise / certification | Not started